## Лист1
Task | Priority | Status | Assignee
1. Reduce count of Gomel-sat news to 45 (3 pages) | ASAP | Done | Arthur
2. Make feature to clear old news | Middle | Open
3. Rename: "header" to "headline" and "piece of news " to "article" | Low | Open
4. Include "Link Generator" as a feature | Middle | Open
5. Search algorithm optimization | Hight | In Progress | Arthur
6. Add feature to format urls | Hight | Open
7. Remove head link "App Gomelsat helper" | Low | Open
8. Add button "Back to list" | Low | Open
9. Feature to download/upload list of words | Hight | Upload feature remained | Arthur
10. Separate gomel-sat and word options | Middle | Open
11. Feature to include header text to common text if don't exist | Hight | Open
12. Feature to search the most "red" news | Middle | Open
13. Fix bug of incorrect div count | Hight | Open